## COH
Updated: 4/13/23
Corridor | Mileage | Design | Construction | Notes
North Main - Boundary to Cottage | 0.7 | 95% Design |  | Awaiting permit from TxDOT; construction initiation after TxDOT provides permit.
North Main - Cottage to Airline | 0.5 | Concept |  | City Council approved funding on 10/11/22. Design work began in Winter 2023.
11th St & Michaux - N Shepherd Dr to Michaux; 11th to Usener St | 1.9 | Complete | In Progress | Studewood and Michaux: street rehab complete; construction of safety improvements underway. Construction of pedestrian refuge island underway at White Oak and Michaux.
Patterson/Blossom/Jackson Hill - White Oak Bayou to Scotland St | 0.9 | 100% Design |  | 100% Design review; Awaiting permit from TxDOT; construction exepected to begin after TxDOT provides the permit.
Shepherd/Durham - Dickson St to Washington Ave | 1.8 | Complete | In Progress
Antoine/Hammerly Roundabout | 0.4 | Concept
Antoine - 290 to W Mt Houston Rd | 4.9 | Concept Complete |  | DCR complete. 30% design upcoming.
Lawndale St - Telephone to Forest Hill Blvd | 2.5 | Complete | Complete | Ribbon cutting was in March 2023.
Westpark - Oxford Oak St to Kirkwood | 1.5 | Complete |  | CIP
Fulton - Quitman to Hogan | 0.9 | 30% Design |  | CIP
Egbert St - TC Jester to Moy | 0.16 | 90% Design |  | Part of larger Cottage Grove East project. Egbert will be an off-street facility.
Detering - Larkin to Egbert | 0.25 | 90% Design |  | Part of larger Cottage Grove East project. Detering will be a shared on-street facility.
Larkin - TC Jester to Detering | 0.12 | 90% Design |  | Part of larger Cottage Grove East project. Larkin between TC Jester and Detering will be a shared on-street facility.
Lockwood Dr - Suburban St to Crites St | 0.17 | 90% Design |  | CIP
Lockwood Dr - Harrisburg Blvd to Suburban St | 0.5 | In Progress |  | CIP. Design underway, coordinating with METRO on the University BRT project.
West Little York - TC Jester to Wheatley | 3.4 | Concept Complete |  | Approved for TxDOT 2020 HSIP funding.
Quitman Overpass - Elysian St to Stevens St | 0.4 | 90% Design |  | This is a HCTRA project that COH is reviewing.
Fondren - Braeswood to Airport | 1.5 | Concept Complete |  | CIP
Parker Rd - Airline to Exeter | 0.5 | 95% Design |  | Finalizing design, including street trees.
Dunvale - Westheimer to Westpark | 1.25 | Concept Complete |  | Design expected to begin in 2024 with construction in 2025.
Irvington - 610 to Hardy Toll Road Frontage | 3.4 | Concept Complete |  | Design expected to begin in 2024 with construction in 2025.
Lawndale - Allen Genoa to Glasgow | 1.1 | Concept Complete |  | Design expected to begin in 2024 with construction in 2025.
Mesa - Caddo to Little York | 1.2 | Concept Complete |  | Design expected to begin in 2024 with construction in 2025.
W Gray - Shepherd to Waugh | 0.9 | Concept Complete |  | Design expected to begin in 2024 with construction in 2025.
Northline - Parker to Canino | 1.3 | Concept Complete |  | Design expected to begin in 2023 with construction in 2024.
Glenmont - Westward to Royalton | 1.5 | Concept Complete |  | Design expected to begin in 2024 with construction in 2025.
W Alabama - Buffalo Speedway to Weslayan | 0.7 | Complete | In Progress | As part of a repaving and drainage project bike lanes and an 8' shared use paths were incorporated into the design. Construction expected to complete in Summer 2023.
Lamar - Bagby to Off Street Trail connection | 0.14 | Concept Complete |  | Design work began in Winter 2023.
TOTAL MILEAGE | 34.49

## PCT1
Harris County PCT One |  |  |  | Updated: April 2023
Corridor | Mileage | Design | Construction | Notes
Future Precinct One
Southeast/MLK | 5.2 | Design Ongoing |  | As of 04/06/23, Project on hold pending community engagement. Segment 1 - 100% Design, pending UH-COH ILA and paving cost share; Segment 2A & 3A 90% Design
Cavalcade/Homestead | 9 | Design Ongoing |  | As of 04/06/23, Project on hold pending community engagement. Segment 1 & 2 - 90%; Segment 3 60% - Design Complete
Hillcroft | 3.6 | Concept Complete |  | Conceptual Design Study Complete
Almeda Shared Use Path | 0.9 | Complete | Substantial Completion | Substantial Completion Inspection complete. Next steps: punchlist completion, TDLR inspection by end May 2023.
El Rio - El Camino | 0.5 | Complete | Ongoing | Estimated completetion May 2023
Trail Fondren Diversion Channel | 0.7 | Complete | Substantial Completion | Substantial Completion
Preston Bikeway | 1 | Concept Complete |  | Conceptual Design Study Complete
CE King Trail | 2.3 | Design Ongoing |  | 30% Concentual Alignment
Fannin/San Jacinto | 5.3 | Concept Ongoing |  | Conceptual Design Study Ongoing
Hill at Sims Phase I | 2.6 | Design Ongoing |  | Trail 100 % Design; Hilltop 75%
Hill at Sims Phase II | 1 | Design Ongoing |  | Conceptual Design Ongoing
Cullen Blvd - UH | 2.1 | Complete | In Progress | Partnership with COH and UH
Blodgett/Tierwester - TSU Phase II | 1 | Complete | In Progress | Partnership with COH and TSU
W. Mount Houston - W. Montgomery - TC Jester | 2.6 | Complete | Substantial Completion | Substantial Completion Inspection complete. Punchlist ongoign.
White Oak Bayou Trail | 10.68 | Complete | In Progress | Under Construction
Trail to Keegans Bayou | 0.3 | Complete | Complete | Complete
Deussen Parkway | 1.5 | Complete | Complete | Complete
Funding Partnership Projects
Montrose Bikeway & Sidewalk | 9.7 | Ongoing | In Progress | Feasiblity Completed on 9.7 miles; Waugh-Commonwealth Complete 2.18mi; Hawthorne-Woodhead Under Construction 3.14mi; Mandell-Dallas Concept Complete 1.2mi;
Midtown - Tuam Bikeway | 0.5 | Complete | Ongoing | Partnership with Midtown TIRZ and COH Waterline Project
54 Scott METRO BOOST | 1.8 | Design Ongoing |  | METRO Lead, Design Ongoing; Agreement in process
18 Miles - 2018-2021 Projects | 18
Lyons |  | Complete | Complete
Hardy-Elysian |  | Complete | Complete
Kelley |  | Complete | Complete
Austin/LaBranch/Crawford |  | Complete | Complete
Hutchins-Cleburne |  | Complete | Complete
Gray |  | Complete | Complete
Polk |  | Complete | Complete
Cullen |  | Complete | Complete
Austin/LaBranch - HCC Realignment |  | Complete |  | Design Complete; on Hold
TOTAL MILEAGE | 80.28
TOTAL COMPLETE | 21.98
TOTAL CONSTRUCTION | 21.62
TOTAL IN STUDY / DESIGN | 36.68

## PCT2
Harris County PCT 2 |  |  |  | Updated: 4/13/23
Corridor | Mileage | Study/Design | Construction | Notes
Visit projects.hcp2.com for more info
*Kowis St. (Aldine) | 0.45 | Complete | In Progress | In construction. Envision certification upcoming
*Freeport St. (Cloverleaf) | 2.4 | Complete | In Progress | Bid Phase
Armand Bayou Trail (Pasadena) | 2 | Complete |  | 100% Design
*Fairmont Pkwy Trail Phase I (Pasadena) | 0.5 | In Progress |  | Study complete
*Fairmont Pkwy Trail Phase II (Pasadena to Laporte) | 6.5 | In Progress |  | Study ongoing
Bay Area Boulevard (Laporte to Clear Lake) | 4.5 | In Progress |  | Improvements to existing bike lane.
Partnership Projects
*Market St (Baytown) | 2.3 | Complete |  | Partnership with City of Baytown. 100% design
*Quitman St. | 1.4 | Complete |  | Partnership with GNMD, COH, METRO. Bid Phase
Buffalo Bend - Hidalgo Greenway | 0.4 | In Progress |  | Partnership with BBP, COH
Navigation Blvd (BBP) | 1 | In Progress |  | Partnership with BBP. Study ongoing
Pinckney St . Trail | 0.15 | Complete |  | Partnership with TIRZ 21. Bid Phase
Vince Bayou Greenway | 1.4 | In Progress |  | Partnership with City of Pasadena, HPB. Permitting Phase
Completed Projects
Hardy-Elysian |  | Complete | Complete | Partnership with Pct. 1, COH
Main St. Trail (Galena Park) |  | Complete | Complete | Partnership with Port Houston and Galena Park
Bay Area Hike and Bike Segment 1 Phase 1 |  | Complete | Complete
Bay Area Hike and Bike Segment 1 Phase 2 |  | Complete | Complete
Bay Area Hike and Bike Segment 3 |  | Complete | Complete
Exploration Green |  | Complete | Complete | Partnership with CLWA
East End Bike Plan | - | Complete | Complete | Partnership with EED
Carpenter's Bayou Trail (Channelview) | 0.8 | Complete | Complete | Construction Complete
Vickery St. (Aldine) | 1 | Complete | Complete | Construction Complete
TOTAL MILEAGE | 24.8

## HPB
Houston Parks Board / Bayous |  |  |  |  | Updated: 4/19/23
Corridor
Buffalo Bayou | Mileage | Design | Permitting | Construction | Notes | Updated
Austin to McKee via Commerce Street and Elysian Viaduct | 0.3 | In Progress |  |  | Design contract for detour along Eysian to be approvd by Board April 2023 | 2023-04-19
Fannin to Austin | 0.2 | Complete | Complete | Complete |  | 2023-04-19
Hunting Bayou
Maxey Rd to Manitou | 4 | Complete | Complete | In Progress | Partial substantial completion, under US90 pending TxDOT rebuilding eroision under freeway bridge open between Manitou and Wallisville and Herman Brown Park to Maxey | 2023-04-19
Sims Bayou | Mileage | Design | Permitting | Construction | Notes
Glenbrook Park to I45 & Reveille Park to Telephone Road | 1 | Complete | Complete | Complete |  | 2023-04-19
Stuart Park to FM Law Park | 3.4 | Complete | Complete | In Progress | Substantial Completion Walk Through April 2023 | 2023-04-19
FM Law Park to MLK | 1.2 | Complete | Complete | In Progress | Construction through Fall 2023 | 2023-04-19
Scott St to Buffalo Spdwy | 5.3 | Complete | Complete | In Progress | Anticipated completion Spring 2023; Detour expected around SH288 pending TxDOT and Blueridge Transportation remedial work | 2023-04-19
Brays Bayou | Mileage | Design | Permitting | Construction | Notes
Mason Park under UPRR bridge (north sides) | 0.3 | Complete | In Progress |  |  | 2023-04-19
Mason Park under UPRR bridge (south sides) | 0.3 | In Progress |  |  |  | 2023-04-19
Holcombe to Stella Link (south side) | 3.7 | Complete | In Progress |  |  | 2023-04-19
Stella Link to S. Rice (south side) | 1.1 | Complete | In Progress |  |  | 2023-04-19
S. Rice to Braeburn Glen (south side) | 3.3 |  |  |  | In planning (pre-design) | 2023-04-19
Chimney Rock to Hillcroft (north side) | 1 | Complete | In Progress |  |  | 2023-04-19
Braeburn Glen to Eldridge | 7.8 | Complete | Complete | In Progress | Issues dealing with CenterPoint and TxDOT; estimated completion end of2023 | 2023-04-19
Halls Bayou | Mileage | Design | Permitting | Construction | Notes
Talton St to Lake Forest Park | 0.4 | Complete | Complete | Complete |  | 2023-04-19
Tidwell to Bretshire/Hirsh to Jensen | 2.4 | Complete | In Progress |  | TxDOT/HPARD Advanced Funding Agreement pending; estimated completion end of 2026 | 2023-04-19
Mesa Dr to Banting St | 1.1 | Complete | Complete | Complete |  | 2023-04-19
San Jacinto Bayou | Mileage | Design | Permitting | Construction | Notes
Woodland Hills to Ross Rd | 2.6 | Complete | Complete | Complete |  | 2023-04-19
White Oak Bayou | Mileage | Design | Permitting | Construction | Notes
MKT Connection | 0.2 | Complete | Complete | Complete |  | 2023-04-19
Extension to Jones Rd (HCFCD Project) |  | Complete | Complete | In Progress | By HCFCD | HCFCD
Utility Corridors | Mileage | Design | Permitting | Construction | Notes
Spring Branch Trail - Wirt to Blalock | 2.4 | Complete | Complete | Complete
Spring Branch Trail - Gessner to Shadowdale Drive | 0.6 | Complete | In Progress |  | for Spring Branch Management District on HOLD for CenterPoint work
Spring Branch Trail - Blalock to Existing Emnora Trail | 0.9 | In Progress |  |  |  | 2023-04-19
Sharpstown Trail - Sands Point to Beechnut | 1.8 | Complete | Complete |  | For TIRZ 20 - on hold awaiting federal earmark funding
Sharpstown Trail - Beechnut to Brays Bayou Greenway | 0.8 | In Progress |  |  | For TIRZ 20
Law Park Connector - Mykawa to CenterPoint | 1.3 | Complete | Complete | In Progress | Construction started January 2023 | 2023-04-19
TOTAL MILEAGE | 47.4

## TxDOT
TxDOT |  |  |  | 2023-04-13
Corridor | Mileage | Design Status | Construction Status | Notes
*I-610 Feeder (12th to NW Transit Center) | 0.5 |  |  | Design start forthcoming; funding move to FY 2024
Trail Connection (MKT to WOB Trail) |  | Complete | Awaiting construction | Projected award date: Jul 28
*I-10 (Cohn to Westcott) | 0.4 | Awaiting Permit |  | Design/documentation submitted for permit to construct under the railroad; funding late FY 2023
East Fwy/Federal/Maxey | 2.2 | Complete | Complete | Complete
TOTAL MILEAGE | 3.1

## METRO
METRO |  |  |  | Updated: 4/17/23
Corridor | Mileage | Design Status | Construction Status | Notes
Cavalcade Phase 2 | 0.6 | Complete | Complete | Accepted by the COH on July 19, 2022.
Leeland |  | Complete | Complete | Accepted by the COH on October 19, 2021.
Quitman | 1.4 | 100% Complete |  | Partnership with COH, Harris County Pct 2. Interlocal Agreement with partners approved by METRO Board in June 2021. METRO, GNMD and Harris County Pct. 2 contributing funds. HC Pct 2 leading design and construction bid. GNMD leading maintenance.
McGowen Bikeway | 1.8 | 95% Complete |  | Main St to Scott St; Part of 54 Scott BOOST project which is a METRONext project. Dedicated on-street
Mainer | 1 | 95% Complete |  | In partnership with Precinct 1. Scott St. to Ardmore (Holly Hall Trail). Dedicated on-street.
TOTAL MILEAGE | 4.8
Note on A9: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Should Airline and Cavalcade as part of BOOST 56 be added? Reply: @Lynn, Virginia - HPW for the most part I've asked Yuhayna & METRO to self report, but I don't see a problem with it. Is there another section of Cavalcade aside from the phase 2 above, and is Airline at design? Reply: Yes it is distinct. They submitted the traffic study for it in March. I think they're entering design soon but I'm not entirely sure. @Hlavacek, Ian - HPW do you know? Reply: Within next 6 months Reply: thanks!

## TIRZ
TIRZ |  |  |  | 2023-04-13
Corridor | Mileage | Design Status | Construction Status | Notes
TIRZ 5 (MHRA)
Shepherd Dr/Durham Dr Ph 1 (15th to I-610) | 2.4 | Complete | In progress | Installation of Water and Wastewater has started. Centerpoint still has not started poll relocation. We have issued a change order to start construction using a different method to allow the project to go forward while Centerpoint moves polls. First section of project 15th to 20th should take approximately 1 year
Shepherd Dr/Durham Dr Ph 2 (15th to I-10) | 2.8 | In Progress |  | Expected construction Q4 FY 2024
MKT Improvements (Houston Ave to Termination) | 0.1 | Complete | In Progress | Significant progress made. Waiting on striping and signage.
Heights (Center to IH-10) | 0.4 | Complete | Construction started 3/28 | Also includes intersection improvements at Washington/Waugh and Washington/Center;
W Dallas (Dunlavy to Waugh) | 0.3 | Complete | Complete
W Dallas (Tirrel to Dunlavy) | 0.1 | Complete | In Progress | Expected construction Q1-Q2 FY 2023 Developer Reimbursement Project - there will be an interim phase and a final phse (FY 24)
W Dallas (Shepherd to Tirrel) | 0.3 | Complete | Complete
WOB Trail to Memorial (Moy St to Kansas St) | 0.1 | Complete | Construction Complete | trail complete - trees will be planted in Fall this year or Spring of 23 - still working with the City to define maintenance responsibility and schedule
Downtown TIRZ
Bagby/Dallas | 0.7
TIRZ 27 (Montrose)
Waugh/Yoakum/Commonwealth/Lovett | 2.2 | Complete | In Progress
Hawthorne/Woodhead |  | In Progress
Dallas Bikeway |  | In Progress |  | Expected construction start FY 2023
Welch Stanford |  | In Progress |  | Expected construction start FY 2024
Mandell |  | In Progress |  | Expected construction start FY 2024/2025
TIRZ 17
Briar Branch Trail | 1 | Complete | In Progress
TIRZ 15 (EDRA)
Bastrop Trail (McKinney to Polk) |  | Complete | Complete
Bastrop Trail (Polk to Bell) | 0.1 | In Progress |  | Expected construction: FY 2024
Columbia Tap (St Charles – Ennis) |  | In Progress |  | Expected construction late FY 2023/ FY 2024
Walker (Emancipation to St Emanuel) |  | In Progress |  | Expected construction: FY 2023/FY 2024
TIRZ 13 (OSWRA)
Sawyer (Washington to Memorial/Buffalo Bayou Park) | 0.2 | In Progress |  | Expected construction FY 2023
Edwards (Silver to Sawyer) | 0.3 | In Progress |  | Expected construction FY 2023
Clear Lake Water Authority
Clear Lake Trails | 3.1
TOTAL MILEAGE | 14.1