## COH
City of Houston |  |  |  |  | Updated: 10/13/23
Corridor | Mileage | Design | Construction | Bicycle Facility Type | Notes | Project Page
11th St & Michaux - N Shepherd Dr to Michaux; 11th to Usener St | 1.9 | Complete | Complete | On-street protected bike lane and shared on-street | Heights floating bus stop removal and protected bike lane installation reached substantial completion on 10/13/2023. | https://www.letstalkhouston.org/11th-street-bikeway
Antoine - 290 to W Mt Houston Rd | 4.9 | Concept Complete |  |  | DCR complete. 30% design upcoming.
Antoine/Hammerly Roundabout | 0.4 | Concept
Commerce St - St Charles to Velasco | 0.4 | 90% Design |  | On-street protected bike lane | HPW is designing as part of an asphalt mill and overlay project. The rail tracks will be removed.
Dunvale - Westheimer to Westpark | 1.25 | Concept Complete |  |  | Design expected to begin in 2024 with construction in 2025.
Fondren - Braeswood to Airport | 1.5 | 30% Design |  | Off-street (TBD type) | CIP. Project is currently pending approval from TxDot on the Advance Funding Agreement. | https://www.engagehouston.org/fondren-road-paving-and-drainage-from-braeswood-to-creekbend-and-creekbend-to-w-airport
Fulton - Quitman to Hogan | 0.9 | 30% Design |  |  | CIP Near Northside Road Improvement Project 2
Glenmont - Westward to Royalton | 1.5 | Concept Complete |  |  | Design expected to begin in 2024 with construction in 2025.
Irvington - 610 to Hardy Toll Road Frontage | 3.4 | Concept Complete |  |  | Design expected to begin in 2024 with construction in 2025.
Lamar - Bagby to Off Street Trail connection | 0.14 | Concept Complete
Lawndale - Allen Genoa to Glasgow | 1.1 | Concept Complete |  |  | Design expected to begin in 2024 with construction in 2025.
Lockwood Dr - Harrisburg Blvd to Suburban St | 0.5 | In Progress |  | Shared-use Path | CIP. Design underway, coordinating with METRO on the University BRT project.
Lockwood Dr - Suburban St to Crites St | 0.17 | 100% Design |  | Shared-use Path | CIP. Project is at 100% design completion and construction contract award is anticipated for fall 2023 (April update). | https://www.engagehouston.org/southlockwood1
Mesa - Caddo to Little York | 1.2 | Concept Complete |  |  | Design expected to begin in 2024 with construction in 2025.
North Main - Boundary to Cottage | 0.7 | 95% Design |  | On-street protected bike lane | Awaiting contract issues with construction company to be resolved before construction can begin. | https://www.letstalkhouston.org/north-main
North Main - Cottage to Airline | 0.5 | 90% Design |  | On-street protected bike lane | City Council approved funding on 10/11/22. Most recent public meeting held on August 2. Design expected to be completed in the fall and construction expected to begin in winter 2024. | https://www.letstalkhouston.org/north-main
Northline - Parker to Canino | 1.3 | Concept Complete |  |  | Design expected to begin in 2023 with construction in 2024.
Parker Rd - Airline to Exeter | 0.5 | 95% Design |  | On-street protected bike lane | Finalizing design, including street trees; Awaiting contract issues with construction company to be resolved before construction can begin. | https://www.letstalkhouston.org/parker-road-mobility-project
Patterson/Blossom/Jackson Hill - White Oak Bayou to Scotland St | 0.9 | 100% Design |  | Shared Street/ Neighborhood bikeway | 100% Design; Awaiting contract issues with construction company to be resolved before construction can begin. | https://houstonbikeplan.org/patterson-street/
Polk St - Cullen to S Lockwood Dr | 0.5 | 90% Design | In Progress | On-street protected bike lane | HPW is installing a facility with mountable curb barrier (to maintain heavy trash pickup) as part of an asphalt mill and overlay project. Construction is expected to finish in fall 2023.
Shepherd/Durham - Dickson St to Washington Ave | 1.8 | Complete | In Progress | On-street protected bike lane | Construction is 90% complete as of April 2023. | https://www.engagehouston.org/shepherdanddurham
Tuam - Main to Crawford | 0.4 | 100% Design |  | On-street unprotected bike lane and Shared/neighborhood bikeway | Bike lane with no protection or buffer between Main and Caroline St. Shared vehicle/bike lane between Caroline St and Crawford St. Incorporated into Capital Project 72" water line project. | https://www.engagehouston.org/crawford-to-mt-vernon
W Alabama - Buffalo Speedway to Weslayan | 0.7 | Complete | In Progress | Shared-use Path & on-street unprotected bike lanes | As part of a repaving and drainage project bike lanes and an 8' shared use paths were incorporated into the design. Construction is ongoing. | https://www.engagehouston.org/westalabama
W Gray - Shepherd to Waugh | 0.9 | Concept Complete |  |  | Design expected to begin in 2024 with construction in 2025.
West Little York - TC Jester to Wheatley | 3.4 | Concept Complete |  |  | Approved for TxDOT 2020 HSIP funding.
Westpark - HCFCD D129-01-00 (near Shardowbriar Dr) to Wilcrest Dr | 1.58 | Complete | In Progress | Shared-use paths and on-street protected bike lanes | CIP. Shared-use paths from HCFCD D129-01-00 to West Houston Center Blvd. On-street protected lane (east-bound) and shared-use path (west-bound) from West Houston Center Blvd to Royal Oaks Country Club. On-street protected from Royal Oaks Country Club to Wilcrest. | https://www.engagehouston.org/westpark-paving-and-drainage
TOTAL MILEAGE | 32.44

## PCT1
Harris County PCT One |  |  |  |  | Updated: 10/17/2023
Corridor | Mileage | Design | Construction | Bicycle Facility Type | Notes | Project Page
Future Precinct One
Southeast/MLK | 5.2 | Design Ongoing |  |  | As of 04/06/23, Project on hold pending community engagement. Segment 1 - 100% Design, pending UH-COH ILA and paving cost share; Segment 2A & 3A 90% Design
Cavalcade/Homestead | 9 | Design Ongoing |  |  | As of 04/06/23, Project on hold pending community engagement. Segment 1 & 2 - 90%; Segment 3 60% - Design Complete
Hillcroft | 3.6 | Concept Complete |  |  | Conceptual Design Study Complete
Almeda Shared Use Path | 0.9 | Complete | Substantial Completion |  | Substantial Completion Inspection complete. Next steps: punchlist completion, TDLR inspection by end May 2023.
El Rio - El Camino | 0.5 | Complete | Ongoing |  | Estimated completetion May 2023
Trail Fondren Diversion Channel | 0.7 | Complete | Substantial Completion |  | Substantial Completion
Preston Bikeway | 1 | Concept Complete |  |  | Conceptual Design Study Complete
CE King Trail | 2.3 | Design Ongoing |  |  | 30% Concentual Alignment
Fannin/San Jacinto | 5.3 | Concept Ongoing |  |  | Conceptual Design Study Ongoing
Hill at Sims Phase I | 2.6 | Design Ongoing |  |  | Trail 100 % Design; Hilltop 75%
Hill at Sims Phase II | 1 | Design Ongoing |  |  | Conceptual Design Ongoing
Cullen Blvd - UH | 2.1 | Complete | In Progress |  | Partnership with COH and UH
Blodgett/Tierwester - TSU Phase II | 1 | Complete | In Progress |  | Partnership with COH and TSU Blodgett 95% Complete
W. Mount Houston - W. Montgomery - TC Jester | 2.6 | Complete | Substantial Completion |  | Substantial Completion Inspection complete. Punchlist ongoign.
White Oak Bayou Trail | 10.68 | Complete | In Progress |  | Under Construction
Trail to Keegans Bayou | 0.3 | Complete | Complete |  | Complete
Deussen Parkway | 1.5 | Complete | Complete |  | Complete
Funding Partnership Projects
Montrose Bikeway & Sidewalk | 9.7 | Ongoing | In Progress |  | Feasiblity Completed on 9.7 miles; Waugh-Commonwealth Complete 2.18mi; Hawthorne-Woodhead Under Construction 3.14mi; Mandell-Dallas Concept Complete 1.2mi;
Midtown - Tuam Bikeway | 0.5 | Complete | Ongoing |  | Partnership with Midtown TIRZ and COH Waterline Project
54 Scott METRO BOOST | 1.8 | Design Ongoing |  |  | METRO Lead, Design Ongoing; Agreement in process
TOTAL MILEAGE | 62.28
TOTAL COMPLETE | 1.8
TOTAL CONSTRUCTION | 18.48
TOTAL IN STUDY / DESIGN | 42

## PCT2
Harris County PCT 2 |  |  |  |  | Updated: 10/04/23
Corridor | Mileage | Study/Design | Construction | Bicycle Facility Type | Notes | Project Page
Visit projects.hcp2.com for more info
*Kowis St. (Aldine) | 0.45 | Complete | Complete |  | Substantially complete. Envision certification upcoming. Ribbon cutting Jan 2024
*Freeport St. (Cloverleaf) | 2.4 | Complete | In Progress |  | 50% Construction Complete
Armand Bayou Trail (Pasadena) | 2 | Complete |  |  | 100% Design; Awaiting ROW
*Fairmont Pkwy Trail Phase I (Pasadena) | 0.5 | Complete | In Progress |  | Contractor NTP September 2023
*Fairmont Pkwy Trail Phase II (Pasadena to Laporte) | 6.5 | In Progress |  |  | Study ongoing
Bay Area Boulevard (Laporte to Clear Lake) | 4.5 | In Progress |  |  | Improvements to existing bike lane.
Partnership Projects
*Market St (Baytown) | 2.3 | Complete |  |  | Partnership with City of Baytown. 100% design
*Quitman St. | 1.4 | Complete |  |  | Partnership with GNMD, COH, METRO. Bid Phase
Buffalo Bend - Hidalgo Greenway | 0.4 | In Progress |  |  | Partnership with BBP, COH
Navigation Blvd (BBP) | 1 | In Progress |  |  | Partnership with BBP. Study ongoing
Pinckney St . Trail | 0.15 | Complete |  |  | Partnership with TIRZ 21. Bid Phase
Vince Bayou Greenway | 1.4 | In Progress |  |  | Partnership with City of Pasadena, HPB. Permitting Phase
Completed Projects
Hardy-Elysian |  | Complete | Complete |  | Partnership with Pct. 1, COH
Main St. Trail (Galena Park) |  | Complete | Complete |  | Partnership with Port Houston and Galena Park
Bay Area Hike and Bike Segment 1 Phase 1 |  | Complete | Complete
Bay Area Hike and Bike Segment 1 Phase 2 |  | Complete | Complete
Bay Area Hike and Bike Segment 3 |  | Complete | Complete
Exploration Green |  | Complete | Complete |  | Partnership with CLWA
East End Bike Plan | - | Complete | Complete |  | Partnership with EED
Carpenter's Bayou Trail (Channelview) | 0.8 | Complete | Complete |  | Construction Complete
Vickery St. (Aldine) | 1 | Complete | Complete |  | Construction Complete
TOTAL MILEAGE | 24.8

## HPB
Houston Parks Board / Bayous |  | Houston Parks Board |  |  |  | Updated: 7/21/23
Corridor
Buffalo Bayou | Mileage | Design | Permitting | Construction | Bicycle Facility Type | Notes | Project Page | Updated
Austin to McKee via Commerce Street and Elysian Viaduct | 0.3 | In Progress |  |  |  | Working towards permit set submittal by end August. |  | 2023-07-25
Hunting Bayou
Maxey Rd to Manitou | 4 | Complete | Complete | In Progress |  | Partial substantial completion, under US90 pending TxDOT rebuilding erosion under freeway bridge open between Manitou and Wallisville and Herman Brown Park to Maxey
Sims Bayou | Mileage | Design | Permitting | Construction |  | Notes
Stuart Park to FM Law Park | 3.4 | Complete | Complete | Complete |  |  |  | 2023-07-25
FM Law Park to MLK | 1.2 | Complete | Complete | In Progress |  | Construction through Fall 2023
Scott St to Buffalo Spdwy | 5.3 | Complete | Complete | Complete/In Progress |  | Complete except for area under SH288 pending TxDOT work. Detour open through Margaret Jenkins Park, west along Airport and south through Houston Sports Park. |  | 2023-07-25
Brays Bayou | Mileage | Design | Permitting | Construction |  | Notes
Mason Park under UPRR bridge (north sides) | 0.3 | Complete | In Progress |  |  |  |  | 2023-07-25
Mason Park under UPRR bridge (south sides) | 0.3 | In Progress | [5 empty] | 2023-07-25
Holcombe to Stella Link (south side) | 3.7 | Complete | In Progress |  |  |  |  | 2023-07-25
Stella Link to S. Rice (south side) | 1.1 | Complete | In Progress |  |  |  |  | 2023-07-25
S. Rice to Braeburn Glen (south side) | 3.3 | In Progress | [5 empty] | 2023-07-25
Chimney Rock to Hillcroft (north side) | 1 | Complete | In Progress |  |  |  |  | 2023-07-25
Braeburn Glen to Eldridge | 7.8 | Complete | Complete | In Progress |  | Issues dealing with CenterPoint and TxDOT; estimated completion end of 2023
Halls Bayou | Mileage | Design | Permitting | Construction |  | Notes
Tidwell to Bretshire/Hirsh to Jensen | 2.4 | Complete | In Progress |  |  | TxDOT/HPARD Advanced Funding Agreement pending; estimated completion end of 2026
White Oak Bayou | Mileage | Design | Permitting | Construction |  | Notes
Extension to Jones Rd (HCFCD Project) |  | Complete | Complete | In Progress |  | By HCFCD |  | HCFCD
Utility Corridors | Mileage | Design | Permitting | Construction |  | Notes
Spring Branch Trail - Gessner to Shadowdale Drive | 0.6 | Complete | In Progress |  |  | for Spring Branch Management District on HOLD for CenterPoint work |  | 2023-07-21
Spring Branch Trail - Blalock to Existing Emnora Trail | 0.9 | In Progress |  |  |  | for Spring Branch Management District |  | 2023-07-21
Sharpstown Trail - Sands Point to Beechnut | 1.8 | Complete | Complete |  |  | For TIRZ 20 - bidding slated to start in August |  | 2023-07-21
Sharpstown Trail - Beechnut to Brays Bayou Greenway | 0.8 | Complete | In Progress |  |  | For TIRZ 20 |  | 2023-07-21
Law Park Connector - Mykawa to CenterPoint | 1.3 | Complete | Complete | In Progress |  | Construction 85% complete. |  | 2023-07-25
TOTAL MILEAGE | 39.5

## TxDOT
TxDOT |  |  |  |  | 2023-10-04
Corridor | Mileage | Design | Construction | Bicycle Facility Type | Notes | Project Page
*I-610 Feeder (12th to NW Transit Center) | 0.5 |  |  |  | Design start forthcoming; funding move to FY 2024
Trail Connection (MKT to WOB Trail) |  | Complete | Awaiting construction |  | Projected award date: Jul 28
*I-10 (Cohn to Westcott) | 0.4 | Awaiting Permit |  |  | Design/documentation submitted for permit to construct under the railroad; funding late FY 2023
SH 3 (Richey St. to FM 518) | 14 | Complete | Complete |  | This is a buffered bike lane. It goes all the way south to League City.
TOTAL MILEAGE | 14.9

## METRO
METRO |  |  |  |  | Updated: 7/25/23
Corridor | Mileage | Design | Construction | Bicycle Facility Type | Notes | Project Page
Quitman | 1.4 | 100% Complete |  |  | Partnership with COH, Harris County Pct 2. Interlocal Agreement with partners approved by METRO Board in June 2021. METRO, GNMD and Harris County Pct. 2 contributing funds. HC Pct 2 leading design and construction bid. GNMD leading maintenance.
McGowen Bikeway | 1.8 | Complete |  |  | Main St to Scott St; Part of 54 Scott BOOST project which is a METRONext project. Dedicated on-street. construction to begin August 2023
Mainer | 1 | 95% Complete |  |  | In partnership with Precinct 1. Scott St. to Ardmore (Holly Hall Trail). Dedicated on-street.
TOTAL MILEAGE | 4.2
Note on A7: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Should Airline and Cavalcade as part of BOOST 56 be added? Reply: @Lynn, Virginia - HPW for the most part I've asked Yuhayna & METRO to self report, but I don't see a problem with it. Is there another section of Cavalcade aside from the phase 2 above, and is Airline at design? Reply: Yes it is distinct. They submitted the traffic study for it in March. I think they're entering design soon but I'm not entirely sure. @Hlavacek, Ian - HPW do you know? Reply: Within next 6 months Reply: thanks!

## TIRZ
TIRZ |  |  |  |  | 2023-10-18
Corridor | Mileage | Design Status | Construction Status | Bicycle Facility Type | Notes | Project Page
TIRZ 5 (MHRA)
Shepherd Dr/Durham Dr Ph 1 (15th to I-610) | 2.4 | Complete | In progress |  | Bike lanes and sidewalk installation - 15th -20th of both Shepherd and Durham has started. Streetlights with pedestrian/bikeway light installation has also started.
Shepherd Dr/Durham Dr Ph 2 (15th to I-10) | 2.8 | In Progress |  |  | Expected construction start Q4 FY 2024
MKT Improvements (Houston Ave to Shepherd | 0.1 | Complete | Complete
Heights (Center to IH-10) | 0.4 | Complete | Complete
W Dallas (Dunlavy to Waugh) | 0.3 | Complete | Complete
W Dallas (Tirrel to Dunlavy) | 0.1 | Complete | in Progress |  | Bike lanes from Tirell to Dunlavy are in- there will be an improvement to add separation after the development north of Dallas is complete. The development will probably take something like 2 years. They are not installing separation at this time because it will be damaged during construction.
W Dallas (Shepherd to Tirrel) | 0.3 | Complete | Complete
WOB Trail to Memorial (Moy St to Kansas St) | 0.1 | Complete | Construction Complete
Downtown TIRZ
Bagby/Dallas | 0.7
TIRZ 27 (Montrose)
Waugh/Yoakum/Commonwealth/Lovett | 2.2 | Complete | In Progress
Hawthorne/Woodhead |  | In Progress
Dallas Bikeway |  | In Progress |  |  | Expected construction start FY 2023
Welch Stanford |  | In Progress |  |  | Expected construction start FY 2024
Mandell |  | In Progress |  |  | Expected construction start FY 2024/2025
TIRZ 17
Briar Branch Trail | 1 | Complete | In Progress
TIRZ 15 (EDRA)
Bastrop Trail (McKinney to Polk) |  | Complete | Complete
Bastrop Trail (Polk to Bell) | 0.1 | In Progress |  |  | Expected construction: FY 2024
Columbia Tap (St Charles – Ennis) |  | In Progress |  |  | Expected construction late FY 2023/ FY 2024
Walker (Emancipation to St Emanuel) |  | Complete | In Progress |  | Expected construction: FY 2023/FY 2024
TIRZ 13 (OSWRA)
Sawyer (Washington to Memorial/Buffalo Bayou Park) | 0.2 | In Progress |  |  | Expected construction FY 2023
Edwards (Silver to Sawyer) | 0.3 | In Progress |  |  | Expected construction FY 2023
Clear Lake Water Authority
Clear Lake Trails | 3.1
TOTAL MILEAGE | 14.1